## Sheet1
Week 2
Product Owner | SCRUM Master | SCRUM Team
Amit chandane | Arpit Kumar | Anshika
Amar Kumal
Abhishek Gupta
Aishwarya Jadhav
Anand Waghmare
Amit Nivargi
Ajinkya Ingle

## Sprint Backlog
ID | User Story | Tasks | Estimate | Owner | Status
US001 | As a borrower, I want to create an account on the platform to access loan services. | Task 1: Design User Friendly UI | 6 | Amar | In progress
|  | Task 2: Gather all the detail requirements | 8 | Amit | In progress
|  | Task 3: Design and initiate homepage . | 12 | Anshika | Not started
|  | Task 4: Implement Forms UI design. | 6 | Arpit | Not started
|  | Task 5: Responsiveness of homepage(All Screen size) | 12 | Abhishek | Not started
US002 | As a borrower, I want to log in securely using my email and password. | Task 6: Analyze proper Database for implementation. | 4 | Abhishek | In progress
|  | Task 7: Analyze Backend flexible languages. | 12 | Ajinkya | In progress
|  | Task 8: Develop backend use cases . | 10 | Anshika | In progress
|  | Task 9: Identify database workloads. | 8 | Aishwarya | Not started
|  | Task 10: Analyze suitable databse for data security point of view. | 14 | Anand | Not started
US003 | As a borrower, I want to view available loan products and their details (interest rates, terms, etc.). | Task 11: Do visit and research on existing loan application. | 5 | Arpit | In progress
|  | Task 12: Collect all the relevant contents. | 6 | Amit | Not started
|  | Task 13: Collaborate with bank for details | 11 | Ajinkya | Not started
|  | Task 14: Accessibility of loan product for ease of borrower | 4 | Anand | In progress
|  | Task 15: Analyze the borrower requirements | 7 | Aishwarya | In progress
US004 | As a borrower, I want to apply for a loan in the loan application, so that I can easily request financing for my needs. | Task 16: Design the Loan Application Form | 6 | Amar | In progress
|  | Task 17: Develop the Loan Application Submission Feature | 4 | Abhishek | In progress
|  | Task 18: Create a Document Upload Module | 6 | Anshika | In progress
|  | Task 19: Implement Application Status Tracking | 8 | Ajinkya | In progress
|  | Task 20: Test the Application Process End-to-End | 12 | Amit | In progress

## Product Backlog
USER STORY ID | USER STORY | Description | Priority | Complexity | Status
US001 | As a borrower, I want to create an account on the platform to access loan services. | Implement user registration functionality with email verification. | Critical | Medium | In Progress
US002 | As a borrower, I want to log in securely using my email and password. | Develop a secure authentication system for user logins and password management. | High | High | In Progress
US003 | As a borrower, I want to reset my password in case I forget it. | Add functionality for password reset via email. | Medium | Medium | Pending
US004 | As a borrower, I want to view available loan products and their details (interest rates, terms, etc.). | Design a user interface for borrowers to browse and view loan products. | High | High | In Progress
US005 | As a borrower, I want to apply for a loan by providing necessary personal and financial information. | Create a loan application form with required fields and validation checks. | Medium | Medium | In Progress
US006 | As a borrower, I want to upload required documents for loan processing (ID proof, income statements, etc.). | Implement a status tracking system for borrowers to monitor their application progress. | Low | Low | Pending
US007 | As a borrower, I want to track the status of my loan application in real-time. | Implement a status tracking system for borrowers to monitor their application progress. | Medium | High | Pending
US008 | As a lender, I want to communicate with borrowers regarding loan offers and application status. | Implement messaging features for lenders and borrowers within the platform. | Low | Medium | In Progress